## Cover
START USING THIS DOCUMENT: See Instructions on How to Use
Implementation plan
Acknowledgment of Aboriginal people and communities in Victoria
The Victorian Government proudly acknowledges Aboriginal people as Australia’s First Peoples and as the Traditional Owners and custodians of the land and waterways upon which we depend. We acknowledge Victoria’s Aboriginal communities and culture and pay respect to their Elders past and present.
Aboriginal culture is founded on a strong social and cultural order that has sustained up to 60,000 years of existence. Victorian Aboriginal communities and peoples are culturally diverse, with rich and varied heritages and histories pre- and post- invasion. The impacts of colonisation — while having devastating effects on the traditional life of Aboriginal Nations — have not diminished Aboriginal people’s connection to country, culture or community.
The Victorian Government recognises the long-standing leadership of Aboriginal communities in Victoria to prevent and respond to family violence, supported through self-determination and self-management, to improve outcomes for Aboriginal people and families, whilst also acknowledging the devastating impacts and accumulation of trauma across generations as a result of colonisation and the dispossession of land and children.
Authorised and published by the Victorian Government, 1 Treasury Place, Melbourne 3002
© State of Victoria, Australia, Family Safety Victoria, June 2020.
ISBN 978-1-76096-065-0 (pdf/online/MS word)
Accessibility
If you would like to receive this publication in an alternative format, please contact 1800 549 646, using the National Relay Service 13 36 77 if required, or email
infosharing@familysafety.vic.gov.au
Content Coordination
Design by Najaaf Saleem
In this document, ‘Aboriginal’ refers to both Aboriginal and Torres Strait Islander people.

## Instructions on How to Use
Implementation plan
Aim of this document
| This template assists you to plan implementation activites | See the blank implementation plan template here
Use this template after completing the MARAM audit tool
| This template is intended to be downloaded and used digitally | See an example completed implementation plan template here
How to use this document
1 | Complete the MARAM audit tool
2 | Identify which of the examples from the MARAM audit tool your organisation wishes to implement next
3 | Add those examples to the implementation plan, identifying all steps
4 | Allocate responsibility for the task
5 | Determine timeframe for completion of the task
Tab B is an example of a partially completed project plan, desmontrating how the assessment in the audit tool translates into tasks on the implementation plan.
Note that:
• each example from the audit tool that is selected for inclusion on the implementation plan may have several steps required to complete it
• the implementation period may be for any determined period – weeks, months or years. Once the tasks identified have been completed, you can return to the audit tool to select your next activity areas
• you may have different implementation plans for different plans, or capture all activities on master implementation plan
• you may plan multiple activities across all four pillars at the same time, or choose to focus on limited activities, dependent upon the capacity of the organisation.

## A - Blank Implementation Plan
IMPLEMENTATION PLAN FINANCIAL YEAR
PROJECT MANAGER ( IF RELEVANT)
| PROGRAM AREA ( IF RELEVANT ) | [5 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16
[7 empty] | 2020-04-20 | [6 empty] | 2020-04-27 | [6 empty] | 2020-05-04 | [6 empty] | 2020-05-11 | [6 empty] | 2020-05-18 | [6 empty] | 2020-05-25 | [6 empty] | 2020-06-01 | [6 empty] | 2020-06-08 | [6 empty] | 2020-06-15 | [6 empty] | 2020-06-22 | [6 empty] | 2020-06-29 | [6 empty] | 2020-07-06 | [6 empty] | 2020-07-13 | [6 empty] | 2020-07-20 | [6 empty] | 2020-07-27 | [6 empty] | 2020-08-03
MARAM Framework implementation plan (illustrative purposes only) | time axis 2020-04-20 to 2020-08-07
# |  | START DATE | END DATE | OWNER | STATUS | NOTES | time axis 2020-04-20 to 2020-08-07
Pillar 1
Pillar 2
Pillar 3
Pillar 4

## B - E.g. partial plan
IMPLEMENTATION PLAN FINANCIAL YEAR
PROJECT MANAGER ( IF RELEVANT)
| PROGRAM AREA ( IF RELEVANT ) | [5 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16
[7 empty] | 2020-04-20 | [6 empty] | 2020-04-27 | [6 empty] | 2020-05-04 | [6 empty] | 2020-05-11 | [6 empty] | 2020-05-18 | [6 empty] | 2020-05-25 | [6 empty] | 2020-06-01 | [6 empty] | 2020-06-08 | [6 empty] | 2020-06-15 | [6 empty] | 2020-06-22 | [6 empty] | 2020-06-29 | [6 empty] | 2020-07-06 | [6 empty] | 2020-07-13 | [6 empty] | 2020-07-20 | [6 empty] | 2020-07-27 | [6 empty] | 2020-08-03
MARAM Framework implementation plan (illustrative purposes only) | time axis 2020-04-20 to 2020-08-07
# |  | START DATE | END DATE | OWNER | STATUS | NOTES | time axis 2020-04-20 to 2020-08-07
Pillar 1
1A | Identify all policies that need FV content added | 2020-04-20 | 2020-05-04 | Nina Bloggs | Complete | 12 key policies identified. See email of 4 May with confirmed list. | bar: 2020-04-20 to 2020-04-24; 2020-04-27 to 2020-05-01; 2020-05-04
1A | Read key documents identified in audit tool and draft text for inclusion into policies | 2020-05-04 | 2020-05-18 | Nina Bloggs with Sally Smith | Complete | See folder saved on H Drive with key notes from reading. | bar: 2020-05-04 to 2020-05-08; 2020-05-11 to 2020-05-15
1A | Draft text for inclusion into policies based on reading above | 2020-05-18 | 2020-06-01 |  | Complete | With senior execs for approval | bar: 2020-05-18 to 2020-05-22; 2020-05-25 to 2020-05-29; 2020-06-01
1A | Approve text for inclusoin into policies | 2020-06-01 | 2020-06-08 | Senior Execs | Delayed | Awaiting further advice | bar: 2020-06-01 to 2020-06-05; 2020-06-08
1A | Update the policies with approved text | 2020-06-08 | 2020-06-12 | Nina Bloggs | Delayed | Awaiting approval by senior execs | bar: 2020-06-08 to 2020-06-12
| Staff communication about inclusion of FV foundational knowledge into policies | TBC |  | Comms team | Planned
Pillar 2
Pillar 3
3A | Schedule workshop with senior leaders for w/c 18 May | 2020-04-20 | 2020-04-24 |  | Complete | bar: 2020-04-20 to 2020-04-24
3A | Review MARAM Framework | 2020-04-20 | 2020-05-08 |  | Complete | bar: 2020-04-20 to 2020-04-24; 2020-04-27 to 2020-05-01; 2020-05-04 to 2020-05-08
3A | Review MARAM practice guides / summaries | 2020-04-20 | 2020-05-08 |  | Complete | bar: 2020-04-20 to 2020-04-24; 2020-04-27 to 2020-05-01; 2020-05-04 to 2020-05-08
3A | Review MARAM responsibilities guide | 2020-04-20 | 2020-05-08 |  | Complete | bar: 2020-04-20 to 2020-04-24; 2020-04-27 to 2020-05-01; 2020-05-04 to 2020-05-08
3A | Review FVIS and CIS Ministerial Guidelines | 2020-04-20 | 2020-05-08 |  | Complete | bar: 2020-04-20 to 2020-04-24; 2020-04-27 to 2020-05-01; 2020-05-04 to 2020-05-08
3A | Update executive briefing slide pack to make relevant to our organisation | 2020-05-11 | 2020-05-18 |  | In Progress | bar: 2020-05-11 to 2020-05-15; 2020-05-18
3A | Deliver workshop to key senior leaders | 2020-05-19 | 2020-05-19 |  | Planned | bar: 2020-05-19
Pillar 4